## Project Scope
FAMILY BRIDGES TELECOM MIGRATION PROJECT
Project Scope & Migration Phases
Phase | Focus Area | Locations | Timeline | Status
Phase 1 | ISP Migration (Priority) | 11th St, 12th St, 13th St, 14th St | Week 1-2 | Pending
Phase 2 | VoIP Deployment (All Sites) | All 6 locations | Week 3-4 | Pending
Phase 3 | Fax & Security Continuity | All locations (Fax ATAs & Bay Alarm) | Week 5 | Pending
Phase 4 | P2P Elimination & VPN Setup | All locations (WAN optimization) | Week 6 | Pending
Phase 5 | ISP Review (Secondary Sites) | Harrison Ave, 1423 Broadway | Week 7-8 | Pending

## Cost Analysis
COST ANALYSIS: CURRENT VS PROPOSED
Monthly & Annual Savings Projection
Service | Current Monthly | Proposed Monthly | Monthly Savings | Annual Savings
ISP (AT&T + Comcast) | 3200 | 1500 | 1700 | 20400
Voice (AT&T PRI) | 1554.2 | 0 | 1554.2 | 18650.4
Fax Bundle | 400 | 200 | 200 | 2400
Phones & PBX Maintenance | 400 | 438.22 | -38.22 | -458.64
TOTAL | 5554.2 | 2138.22 | 3415.98 | 40991.76
ONE-TIME CAPITAL EXPENDITURE
Item | Vendor | Cost | Qty | Total
Intermedia Unite Implementation | ATS (Quote 26244-543) | 5000 | 1 | 5000
AT&T Fiber Installation | AT&T | 2095.98 | 1 | 2095.98
Network Equipment & Cabling | ATS | 1500 | 1 | 1500
Fax ATA Adapters | Included | 500 | 2 | 1000
CAPEX TOTAL |  |  |  | 9595.98
PAYBACK ANALYSIS
Annual Savings: | 40991.76
Capital Investment: | 9595.98
Payback Period (Months): | 2.8091

## Location Inventory
LOCATION INVENTORY & SITE DETAILS
Per-Site Equipment & Service Details
Location | Address | Employees | Phone Qty | Current ISP | Target ISP
14th St (Main) | 275 14th St, Oakland CA | 45 | 38 | AT&T + Comcast | AT&T Fiber + Intermedia
11th St | 168 11th St, Oakland CA | 20 | 8 | AT&T + Comcast | AT&T Fiber + Intermedia
12th St | 250 12th St, Oakland CA | 15 | 6 | Comcast | AT&T Fiber + Intermedia
13th St | 270 13th St, Oakland CA | 12 | 5 | Comcast | AT&T Fiber + Intermedia
Harrison | 1388 Harrison Ave, Oakland CA | 5 | 2 | Comcast | ISP TBD
Broadway | 1423 Broadway, Oakland CA | 3 | 1 | Comcast | ISP TBD
TOTAL |  | 100 | 60
SYSTEM MIGRATION DETAILS
Current PBX System: | Toshiba PBX
Target Phone System: | Intermedia Unite (Cloud-based)
Voice Service: | AT&T PRI → VoIP (Intermedia Unite)
WAN Architecture: | P2P Links → Site-to-Site VPN
Fax Solution: | Comcast Bundle → ATA Adapters (2 included)
Security Monitoring: | Bay Alarm on Comcast → Cellular/IP Path (cost TBD)

## TN Inventory
TELEPHONE NUMBER PORTING PLAN
Comprehensive TN Migration & Inventory
Phone Number | Current Carrier | Target Carrier | Status
510-302-0460 | AT&T PRI | Intermedia Unite | Pending
510-302-0461 | AT&T PRI | Intermedia Unite | Pending
510-302-0462 | AT&T PRI | Intermedia Unite | Pending
510-302-0463 | AT&T PRI | Intermedia Unite | Pending
510-302-0465 | AT&T PRI | Intermedia Unite | Pending
510-350-0803 | AT&T PRI | Intermedia Unite | Pending
510-350-0804 | AT&T PRI | Intermedia Unite | Pending
510-433-1540 | AT&T PRI | Intermedia Unite | Pending
510-433-1541 | AT&T PRI | Intermedia Unite | Pending
510-433-1542 | AT&T PRI | Intermedia Unite | Pending
510-433-1543 | AT&T PRI | Intermedia Unite | Pending
510-839-9671 | AT&T PRI | Intermedia Unite | Pending
510-839-9673 | AT&T PRI | Intermedia Unite | Pending
510-879-2155 | AT&T PRI | Intermedia Unite | Pending
510-879-2156 | AT&T PRI | Intermedia Unite | Pending
SUMMARY
Total TNs to Port: | 15
Carrier: | AT&T (current) to Intermedia Unite
Porting Method: | Electronic LOA via ATS/Intermedia

## Work Log
COLLABORATIVE WORK LOG
Session Notes & Project Progress Tracking
Date | Owner | Activity/Notes | Status
03/01/2026 | Project Team | Project scope finalized, phases defined | Complete
03/01/2026 | Finance | Cost analysis & ROI calculated (3.2 month payback) | Complete
| ATS/Vendor | Quote review 26244-543 (Intermedia implementation) | In Progress
| IT Manager | Site survey at 14th St (main) - 38 phones identified | In Progress
| Facilities | AT&T Fiber availability confirmed for 11th-14th St | In Progress
| Admin | Bay Alarm contact - security monitoring continuity plan | In Progress
|  | PHASE 1: ISP Migration Planning | Pending
|  | PHASE 2: VoIP System Design & Testing | Pending
|  | PHASE 3: Fax & Security Transition | Pending
|  | PHASE 4: WAN Optimization (P2P → VPN) | Pending
|  | PHASE 5: Secondary Site ISP Review | Pending