## Project Scope
CARRIER SERVICE REVIEW — PROJECT SCOPE
14th St · 13th St · Main Office (11th St) · Oakland CA · ATS Pro-IT · 2025 · Confidential
Current MRC | 5554.2 | → Proposed MRC | 865.78 | Monthly Savings | 4688.42
1 PROJECT OVERVIEW
Objective | Remove legacy Toshiba PRI phone systems and Point-to-Point (P2P) fiber circuits at 14th St and 13th St. Replace with AT&T ABF shared fiber internet, Intermedia Unite VoIP, and a Site-to-Site VPN to Main Office.
Core Problem | 14th St and 13th St run Toshiba PRI phones. Internet and voice are bundled on Comcast broadband via P2P to Main Office (11th St). Fax machines and Bay Alarm security systems ride on those same Comcast analog voice lines.
Key Constraint | Fax and Bay Alarm at both sites must stay operational throughout the transition. The Comcast bundle cannot be cut until dedicated replacements for fax and alarm are live and tested.
Internet | AT&T ABF U-verse shared fiber ordered directly at each site — no more P2P dependency for internet access.
Voice | Intermedia Unite VoIP replaces Toshiba PRI. All DIDs to be ported. Fax lines require ATA adapter. Bay Alarm requires re-provisioning to IP-based or cellular monitoring.
Network | Site-to-Site VPN (Cisco Meraki) replaces the P2P fiber link. VPN must be built, tested, and stable before P2P is disconnected.
2 CURRENT STATE — What Exists Today
Site | What's There Now | Problem | Current MRC | Action
14th St (HFC) | Toshiba PRI phones. 23-ch PRI circuit. Comcast broadband + voice bundle (P2P to 11th St). Fax + Bay Alarm on Comcast analog lines. | Legacy PRI = no VoIP. P2P = expensive dedicated link. Voice bundle includes fax and alarm — cannot simply disconnect. | 329.95 | REPLACE ALL
13th St (Hotel Oakland) | Toshiba PRI phones. Comcast broadband + voice bundle (P2P to 11th St). Fax + Bay Alarm on Comcast analog lines. | Same legacy stack as 14th St. Bundled voice supports fax and Bay Alarm security — must be resolved before any cutover. | 434.65 | REPLACE ALL
11th St (Main Office) | Comcast EDI 1Gb dedicated fiber (internet). Comcast Ethernet P2P 1Gb fiber (private link to 14th St + 13th St). Intermedia Unite VoIP already live. | P2P circuits become redundant once remote sites get direct internet + VPN. High MRC with no ongoing value post-migration. | 2798.94 | DISCONNECT P2P
3 PROPOSED STATE — Target Architecture
Site | New Internet | New Voice / Fax / Alarm | New Network | Est. MRC | Savings
14th St (HFC) | AT&T ABF U-verse 500 × 500 Mb symmetrical Direct to site — no P2P | Intermedia Unite VoIP Port all Toshiba PRI DIDs Fax: ATA adapter on VoIP line Bay Alarm: IP monitoring or cellular | Cisco Meraki S2S VPN Tunnel to 11th St Main Office Must be live before P2P cut | 110 | ↓ $220/mo
13th St (Hotel Oakland) | AT&T ABF U-verse 500 × 500 Mb (confirm MX75 for 1Gb) Direct to site — no P2P | Intermedia Unite VoIP Port all Toshiba PRI DIDs Fax: ATA adapter on VoIP line Bay Alarm: IP monitoring or cellular | Cisco Meraki S2S VPN Tunnel to 11th St Main Office Must be live before P2P cut | 362.84 | ↓ $72/mo
11th St (Main Office) | Comcast EDI 1Gb — keep as primary AT&T ABF — evaluate as secondary/backup | Intermedia Unite VoIP — already live No change required | S2S VPN hub for 14th St and 13th St P2P circuits disconnected once VPN confirmed | No change | ↓ $2,688/mo (P2P removed)
|  | Estimated Total Proposed MRC | 865.78 | ↓ $4,688/mo
4 CRITICAL DEPENDENCIES — Must Resolve Before Any Cutover
ID | Dependency | Why It Matters | Owner | Priority | Status
D-01 | Get full DID TN list from Comcast (14th St) | Cannot port phone numbers without the complete list. Submit CSR request immediately. | Telecom Lead | HIGH | Open
D-02 | Audit and document all fax lines at 14th St and 13th St | Fax is on Comcast analog voice. Need ATA adapter per line or move to eFax — cannot cut Comcast until resolved. | IT Lead | HIGH | Open
D-03 | Bay Alarm security re-provisioning at both sites | Alarm system uses Comcast POTS line. Must migrate to IP or cellular monitoring before bundle is disconnected. | IT Lead / Facilities | HIGH | Open
D-04 | Site-to-Site VPN built and tested before P2P disconnect | P2P is the current network backbone. Cutting it before VPN is stable will take both sites offline. | ATS Pro-IT | HIGH | Open
D-05 | AT&T ABF fiber installed and stable at both sites | VoIP and VPN depend on the new internet circuit being live. Shared internet install: 10–15 business days. | ATS Pro-IT | HIGH | Open
D-06 | Meraki MX68 vs MX75 decision at 13th St | MX68 is capped at 500Mb. If 1Gb AT&T is ordered, MX75 must be in place first. | ATS Pro-IT | MEDIUM | Open
D-07 | Intermedia Unite seat count and porting plan (LOA) | Confirm VoIP seats needed. Porting Toshiba PRI DIDs requires signed LOA and 2–4 week porting window. | Telecom Lead | MEDIUM | Open
5 IMPLEMENTATION SEQUENCE — Order Matters
Step | Action | Responsible | Timeline | Gate / Dependency | Status
1 | Submit CSR request — obtain full DID TN list at 14th St | Telecom Lead | Immediately | No gate | Open
2 | Audit fax lines and Bay Alarm at 14th St and 13th St | IT Lead | Immediately | No gate | Open
3 | Contact Bay Alarm — migrate monitoring to IP or cellular | IT Lead / Facilities | Week 1 | Requires audit (Step 2) | Open
4 | Order AT&T ABF fiber at 14th St and 13th St | ATS Pro-IT | Week 1 | After serviceability confirmed | Open
5 | Confirm Meraki MX68 vs MX75 at 13th St — order if needed | ATS Pro-IT | Week 1 | Before AT&T order at 13th St | Open
6 | Design Site-to-Site VPN (14th ↔ 11th, 13th ↔ 11th) | ATS Pro-IT | Week 1–2 | Runs parallel to Steps 4–5 | Open
7 | Deploy and test Site-to-Site VPN at both sites | ATS Pro-IT | Week 3–4 | AT&T fiber live (Step 4) | Open
8 | Provision Intermedia Unite — configure extensions, routing | Telecom / IT | Week 3–4 | Can set up before porting | Open
9 | Port all DIDs from Toshiba PRI to Intermedia Unite (LOA) | Telecom Lead | Week 4 | VPN stable (Step 7) | Open
10 | Configure ATA adapters for fax lines at both sites | IT Lead | Week 4–5 | Before Comcast voice disconnect | Open
11 | Cut over voice — confirm all DIDs live on Intermedia Unite | Telecom / IT | Week 5–6 | Porting done (9), ATA live (10) | Open
12 | Confirm Bay Alarm operational on new circuit | IT Lead / Facilities | Week 5–6 | Before Comcast disconnect | Open
13 | Disconnect Comcast PRI, P2P, and bundled voice | Telecom Lead | Week 6+ | Steps 7, 11, 12 all confirmed | Open
Confidential · Executive Distribution Only · Costs exclude taxes & fees · ATS Pro-IT · 2025

## Carrier Overview
CARRIER OVERVIEW — Site-by-Site Account Inventory
Oakland, CA · ATS Pro-IT · 2025 · Confidential · All costs exclude taxes & fees
Site / Account | Address | Carrier | Service Type | Bandwidth | Monthly MRC | Contract Status | Action
Main Office – 11th St | 168 11th St, Oakland | Comcast | EDI Dedicated Fiber | 1 Gb | 2798.94 | Expired 2017–19 | DISCONNECT
Main Office – 11th St | 168 11th St, Oakland | Comcast | Ethernet P2P Fiber | 1 Gb (to 14th+13th) | (bundled) | Expired 2017–19 | DISCONNECT P2P
HFC – 14th St | 14th St, Oakland | Comcast | Broadband+Voice Bundle, Full PRI | 23-ch PRI | 329.95 | Expired 2017–19 | REPLACE ALL
Harrison St Ctr – 1388 | 1388 Harrison, Oakland | Comcast | Coax Shared Internet | 75 x 15 Mb | 257.3 | Expired 2017–19 | DISCONNECT
Health Home – 1423 Blvd | 1423 Broadway, Oakland | AT&T | ABF U-verse Shared Fiber | 300 x 300 Mb | 100 | Expired 2017–19 | KEEP — Renew
LMCC – 12th St | 12th St, Oakland | Comcast | Coax Ultimate Biz Pkg | 300 x 35 Mb | 484.7 | Expired 2017–19 | KEEP — Renew
Hong Lok Senior Ctr | 11th St, Oakland | Comcast | Coax Biz Starter | 35 x 5 Mb | 321.65 | Expired 2017–19 | DISCONNECT
Hong Fook Harrison | 1388 Harrison, Oakland | Comcast | Coax Ultimate Biz Pkg | 1 Gb x 35 Mb | 430.53 | Expired 2017–19 | DISCONNECT
Hotel Oakland – 13th St | 13th St, Oakland | Comcast | Broadband+Voice Bundle, PRI | 1 Gb x 35 Mb | 434.65 | Expired 2017–19 | REPLACE ALL
Acct #...2093 – 11th St | 11th St, Oakland | Comcast | Unknown — investigate | Unknown | TBD | Unknown | INVESTIGATE
|  |  |  | CURRENT TOTAL MRC | 5554.2
CARRIER SERVICEABILITY STATUS — Verified per site (see grid)
Carrier | Service Type | 11th St | 14th St | 13th St | 1388 Harr. | 1423 Blvd. | 12th St
AT&T ADI | Ded. Fiber | ✓ Green | ✓ Green | ✓ Green | ✓ Green | ✓ Green | ✓ Green
Comcast EDI | Ded. Fiber | ✓ Green | ✓ Green | ✓ Green | ✓ Green | ✓ Green | ✓ Green
Lumen DIA | Ded. Fiber | Not Serviceable | ✓ Green | ✓ Green | ✓ Green | ✓ Green | ✓ Green
Zayo DIA | Ded. Fiber | ✓ Green | ✓ Green | ✓ Green | ✓ Green | ✓ Green | ✓ Green
AT&T ABF | Shared Fiber | ✓ Green | ✓ Green | ✓ Green | ✓ Green | ✓ Green | Not Serviceable
Comcast Coax | Shared Coax | ✓ Green | ✓ Green | ✓ Green | ✓ Green | ✓ Green | ✓ Green
NOTES & KEY INFORMATION
Note
PRIMARY SCOPE — 14th St and 13th St: Toshiba PRI phones + Comcast voice bundle must be fully replaced. P2P circuits to 11th St will be removed once S2S VPN is live.
Fax machines and Bay Alarm security at 14th St and 13th St are on Comcast analog voice lines. These cannot be disconnected until ATA adapters (fax) and cellular/IP monitoring (Bay Alarm) are operational.
AT&T ABF is symmetrical shared fiber supporting analog TN handoff for fax, alarm, and POS devices.
Comcast Coax is asymmetrical. Upgraded network areas support 300x100 Mb. Supports analog TN handoff.
Dedicated fiber (ADI/EDI/DIA) does NOT support analog TNs unless combined with VoIP (PRI/SIP/analog handoff).
Meraki MX68 at 13th St capped at 500Mb. MX75 required if 1Gb AT&T service ordered at that site.
UPS battery backup recommended for all carrier-supplied equipment at all sites.
Install timelines: Shared internet 10–15 business days. Dedicated fiber 30–45 business days after signed contract.
Confidential · For Internal Use · ATS Pro-IT · 2025

## Current & Proposed
CURRENT & PROPOSED — Carrier Cost Comparison
Oakland, CA · ATS Pro-IT · 2025 · Confidential · All costs exclude taxes & fees
Current MRC | 5554.2 | → Proposed MRC | 865.78 | → Monthly Savings | 4688.42 | → Annualized | 56261.04
CURRENT STATE |  |  |  | PROPOSED STATE
Site | Address | Current Service | MRC | Action | Proposed Service | New MRC | Savings/mo
Main Office 11th St | 168 11th St | Comcast EDI 1Gb Ded. Fiber + P2P 1Gb (to 14th+13th) | 2798.94 | DISCONNECT P2P | Keep EDI as primary. P2P removed once S2S VPN is live. | — | ↓ $2,688
HFC – 14th St | 14th St | Comcast Broadband+Voice Bundle, Toshiba PRI 23-ch, P2P to 11th. Fax+Bay Alarm on analog. | 329.95 | REPLACE ALL | AT&T ABF 500x500Mb, Intermedia Unite VoIP, S2S VPN. ATA for fax, cellular for Bay Alarm. | 110 | ↓ $220
Hotel Oakland 13th St | 13th St | Comcast Broadband+Voice Bundle, Toshiba PRI, P2P to 11th. Fax+Bay Alarm on analog. | 434.65 | REPLACE ALL | AT&T ABF 500x500Mb, Intermedia Unite VoIP, S2S VPN. ATA for fax, cellular for Bay Alarm. | 362.84 | ↓ $72
Harrison St Ctr 1388 | 1388 Harr. | Comcast Coax 75x15 Mb | 257.3 | DISCONNECT | AT&T ABF 300x300Mb (consolidate with 1423 acct) | 100 | ↓ $157
Health Home 1423 Blvd | 1423 Blvd. | AT&T ABF U-verse 300x300 Mb | 100 | KEEP — Renew | AT&T ABF 300x300Mb. Renew contract. | 100 | —
LMCC – 12th St | 12th St | Comcast Coax Ultimate 300x35 Mb | 484.7 | KEEP — Renew | Comcast Coax Ult. Pkg. Renew 3-yr term. | 182.94 | ↓ $302
Hong Lok Senior Ctr | 11th St | Comcast Coax Starter 35x5 Mb | 321.65 | DISCONNECT | No replacement needed — disconnect. | 0 | ↓ $322
Hong Fook Harrison | 1388 Harr. | Comcast Coax Ultimate 1Gb x 35 Mb | 430.53 | DISCONNECT | Consolidate with 1423 Blvd account. | 0 | ↓ $431
Acct #2093 – 11th St | 11th St | Unknown — investigation required | TBD | INVESTIGATE | Confirm status; disconnect or port TNs. | TBD | TBD
|  | CURRENT TOTAL | 5554.2 |  | PROPOSED TOTAL | 865.78 | ↓ $4,688/mo
NOTES & ADVISORIES
# | Note
1 | 14th St and 13th St are the primary scope. Toshiba PRI phones and Comcast voice bundles must be fully replaced. Fax and Bay Alarm cannot be cut until replacements are live.
2 | S2S VPN must be deployed and stable before P2P at 11th St is disconnected. P2P is the current network link for 14th St and 13th St.
3 | AT&T ABF pricing excludes taxes & fees. Static IPs (5 usable) = +$30.00/mo per site. Confirm per-site requirement before ordering.
4 | Comcast Ultimate Business Package: +$10.00/mo escalation at Year 2 and Year 3 of 3-year term contract.
5 | Meraki MX68 at 13th St capped at 500Mb throughput. MX75 required if 1Gb AT&T service is ordered.
6 | All analog TNs (fax, alarm, POS) must be audited before disconnecting any Comcast circuit.
7 | Internet redundancy: AT&T wireless failover $25.00/mo. Comcast wireless failover $29.95 + $15.00 equipment/mo.
Confidential · For Internal Use · ATS Pro-IT · 2025

## Address Serviceability
ADDRESS SERVICEABILITY — Carrier Coverage by Site
Oakland, CA · 6 Sites · ATS Pro-IT · 2025 · Serviceability verified per site — see grid below
Carrier / Service | Type | 11th St | 14th St | 13th St | 1388 Harr. | 1423 Blvd. | 12th St
AT&T ADI | Dedicated Fiber | ✓ Green | ✓ Green | ✓ Green | ✓ Green | ✓ Green | ✓ Green
Comcast EDI | Dedicated Fiber | ✓ Green | ✓ Green | ✓ Green | ✓ Green | ✓ Green | ✓ Green
Lumen DIA | Dedicated Fiber | Not Serviceable | ✓ Green | ✓ Green | ✓ Green | ✓ Green | ✓ Green
Zayo DIA | Dedicated Fiber | ✓ Green | ✓ Green | ✓ Green | ✓ Green | ✓ Green | ✓ Green
AT&T ABF | Shared Fiber | ✓ Green | ✓ Green | ✓ Green | ✓ Green | ✓ Green | Not Serviceable
Comcast Coax | Shared Coax | ✓ Green | ✓ Green | ✓ Green | ✓ Green | ✓ Green | ✓ Green
TECHNOLOGY REFERENCE GUIDE
Term | Definition / Notes
ADI / EDI / DIA | Dedicated fiber internet. Same technology — carrier-specific naming only. Does NOT support analog TNs unless combined with VoIP (PRI / SIP / analog handoff).
AT&T ABF (U-verse) | Symmetrical shared fiber (e.g., 300x300 Mb). Supports analog TN handoff for fax, alarm, POS. Recommended replacement at 14th St and 13th St.
Comcast Coax | Asymmetrical shared internet (e.g., 300x35 Mb). Upgraded areas: 300x100 Mb. Supports analog TN handoff. Bundled voice used for fax and Bay Alarm at 14th & 13th.
AT&T ABF Install Time | 10–15 business days after signed contract.
Dedicated Fiber Install Time | 30–45 business days after signed contract. Construction typically covered 100% by carrier.
AT&T TN Pricing | 1st TN: $15.00/mo · Each additional: $24.00/mo · Max 6 TNs. Excludes taxes & fees.
Comcast TN Pricing | 1st TN included in Ultimate Business Package · Each additional: $24.95/mo. Excludes taxes & fees.
Internet Redundancy | Best practice: secondary ISP at each location. Wireless failover: AT&T $25.00/mo · Comcast $29.95 + $15.00 equipment/mo. Internet only — no TN support.
UPS Battery Backup | Recommended for all carrier-supplied equipment at every site to maintain uptime during power outages.
Construction Costs | Dedicated fiber: carrier typically covers 100%. Shared: partial. Customer may reject any cost — contract canceled without penalty.
SERVICEABILITY COLOR LEGEND
Status | Meaning | Dedicated Fiber Timeline | Shared Internet Timeline
Green | Serviceable — little or no construction | 30–45 business days | 10–15 business days
Yellow | Serviceable — light to moderate construction | TBD after onsite survey | TBD after onsite survey
Orange | Serviceable — moderate to major construction | TBD after onsite survey | TBD after onsite survey
Red | Unserviceable | N/A | N/A
Confidential · For Internal Use · ATS Pro-IT · 2025

## Claude Log
Turn # | Date | User Request | Action Taken | Details | Outcome
1 | 2025-03-01 | User asked to document the project scope across 3 sheets (Carrier Overview, Current & Proposed, Address Serviceability) and build a clean scope sheet 'as I see fit' in the style of a JP Morgan accountant. | Read all 3 sheets in full; created new 'Project Scope' tab (position 0) | Built 7-section structured scope doc: (1) Project Overview, (2) Location Inventory (10 sites), (3) Proposed Target Architecture (6 sites), (4) Cost Summary ($5,554 → $865 MRC, $4,688 savings), (5) Key Issues & Risks (10 items), (6) Technology Notes (9 terms), (7) Recommended Next Steps (11 action items). Applied JP Morgan-style color coding, borders, freeze panes. | Project Scope sheet created and active as tab 1. All three source sheets preserved. Claude Log initialized.
2 | 2025-03-01 | User asked to polish the entire spreadsheet for an executive meeting on Monday. Project Scope sheet was empty (content didn't persist from Turn 1). | Rebuilt Project Scope sheet from scratch with working Office.js border API; polished all 3 source sheets with title banners, freeze panes, and Calibri font. | Project Scope: 6-section exec doc (Exec Summary, Financial Snapshot, Location Inventory, Proposed Architecture, Risks, Next Steps). Borders applied using Excel.BorderIndex enums. Source sheets: inserted 3-row title banners with dark navy + savings-green headers, froze top 3 rows on all sheets. | All 4 sheets polished and presentation-ready. Project Scope tab is Tab 1. Financial savings callout ($4,688/mo) prominently displayed on Current & Proposed banner.
3 | 2025-03-01 | User said Project Scope was hard to read/understand and asked for a 10/10 rebuild for Monday executive meeting. | Fully rebuilt Project Scope sheet with executive-grade design: KPI banner, gold accent column, color-coded accent bars per section, proper number formatting, improved typography and whitespace. | Key upgrades: (1) KPI banner row with $5,554→$865→$4,688 savings in large font; (2) Gold left-edge accent column throughout; (3) Color-coded accent bars — blue for summary/inventory, green for proposed, red/yellow/green for risk priorities; (4) Number cells formatted as $#,##0.00; (5) Increased row heights + wrap text for breathing room; (6) Immediate steps highlighted in red; (7) Navy #002147 footer. Verified render via get_cell_ranges. | Project Scope rebuilt at row 71. KPI banner live. All 6 sections structured and color-coded. Freeze panes on rows 1-3.
4 | 2025-03-01 | User said the scope was too colorful, wants minimalist design, and gave the real project brief: 14th St and 13th St have Toshiba PRI + P2P to Main Office. Goal is to remove P2P + PRI, replace with AT&T ABF fiber, Intermedia Unite VoIP, Site-to-Site VPN. Complication: fax and Bay Alarm security are on the Comcast bundled voice lines. | Fully rebuilt Project Scope sheet with minimalist black/white/grey palette and restructured around the actual project: P2P removal, PRI replacement, VoIP migration, S2S VPN, and fax/Bay Alarm dependency. | Palette: near-black navy headers, white/light-grey body, dark green for savings, dark red for HIGH priority. 5 sections: (1) Project Overview, (2) Current State with fax/alarm detail, (3) Proposed State with per-site internet/voice/network breakdown, (4) Critical Dependencies with D-01 through D-07 including fax and Bay Alarm, (5) 13-step Implementation Sequence with gates. Steps 1 & 2 flagged IMMEDIATELY in red. | Project Scope rebuilt at row 52. Minimalist. Accurate to actual project. Fax/alarm dependency prominently documented. Freeze panes rows 1-2.
5 | 2025-03-01 | User requested final 10/10 polish of all sheets in the workbook for Monday executive meeting. | Rebuilt all 4 sheets (Carrier Overview, Current & Proposed, Address Serviceability, Project Scope) with consistent minimalist design system. Applied tab colors and enforced tab order. | Design system: near-black navy (#1A1A2E) headers, white/light-grey alternating rows, dark green for savings/positive, dark red for DISCONNECT/HIGH-priority, Calibri font throughout. Every sheet: title banner, sub-banner, KPI strip (where applicable), bordered data tables, notes section, footer. All sheets freeze rows 1-2. Tab color #1A1A2E on all 4 tabs. Project Scope fixed as Tab 1. | All 4 sheets rebuilt and consistent. Carrier Overview: 10 sites + serviceability + notes. Current & Proposed: side-by-side comparison + $4,688/mo savings callout + 7 notes. Address Serviceability: 6-site grid + tech reference + color legend. Project Scope: 5-section exec brief. Ready for Monday.
6 | 2025-03-01 | User caught two serviceability errors: (1) Lumen DIA shown as Green at 11th St — actually not serviceable. (2) AT&T ABF shown as Green at 12th St — actually not serviceable. | Corrected both cells in Carrier Overview and Address Serviceability grids. Added cell notes explaining each. Updated section headers. | Carrier Overview: D21 (Lumen @ 11th St) → 'Not Serviceable' red. I22 (AT&T ABF @ 12th St) → 'Not Serviceable' red. Section title changed from 'All Sites Green Flagged' to 'Verified per site'. Address Serviceability: same corrections in grid + title banner corrected from 'ALL SITES GREEN FLAGGED' to neutral. Cell notes added to both corrected cells with explanation. | Errors corrected. Both sheets now reflect accurate serviceability. User to continue reviewing for further issues.
7 | 2025-01-01 | User made manual corrections to Address Serviceability cells and said 'there are so many mistakes' — asked for full spreadsheet fix. | Read full state of all sheets. Synced Carrier Overview serviceability grid to match user corrections. Split Lumen/Zayo DIA into two separate rows. Applied correct green/red formatting to all cells. | User corrections confirmed: Lumen DIA = Not Serviceable at 11th St; AT&T ABF = Not Serviceable at 12th St. All other carriers marked serviceable at all sites. Carrier Overview now has 6 rows (AT&T ADI, Comcast EDI, Lumen DIA, Zayo DIA, AT&T ABF, Comcast Coax) matching Address Serviceability. | Address Serviceability grid: fully formatted and verified. Carrier Overview grid: split and corrected. Awaiting user review of remaining sheets (Current & Proposed, Project Scope).